**MPH Dissertation Time Plan and Evaluation of Progress**

**Student Name:** David O’Hagan

**Date:**  1st May 2023

This form should be updated by the student and sent to [lenath@liverpool.ac.uk](mailto:lenath@liverpool.ac.uk), CC’ing in your supervisor by the 1st of every month. The student’s monthly progress will be monitored by the MPH Programme team.

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Target Date** | **Date Achieved** | **Comments from Student / Supervisor** |
| Proposal signed off by core team | 1/5/22 | 14/2/23 | Change from initial proposal, great support in developing more detailed and focused proposal |
| Ethical approval applied for  (state which Committee) | 2/3/23 | 2/3/23 | completed |
| Ethical approval obtained | 2/3/23 | 2/3/23 |  |
| Other necessary approval obtained (e.g. to access data for MPH dissertation) | 2/3/23 | 2/3/23 |  |
| Start data collection | 2/3/23 | 2/3/23 | complete |
| Complete data collection | 2/3/23 | 2/3/23 | complete |
| Start analyses of data | 2/3/23 | 2/3/23 | Complete |
| Complete analyses of data | 2/5/23 |  | Data clearly set out, with a range of analyses available to fit argument as develops |
| Complete literature review with specified search strategy | 2/6/23 |  | Increasing narrative round references argument developing clarity |
| Complete write up of positionality and epistemology | 2/6/23 |  | initial Draft completed |
| Complete write up of background and introduction | 15/6/23 |  | Beginning of structure, and outline plan completed |
| Complete write up of method | 30/4/23 | 30/4/23 | Has been reviewed and suggestions included. |
| Complete write up of results | 15/4/23 | 30/4/23 | Sent in for review 30/4/23 |
| Complete write up of discussion | 30/5/23 |  | Outline structure only |
| Final draft sent to supervisor | 30/6/23 |  |  |
| Submit dissertation | 20/7/23 |  |  |

**Further explanation of any deadlines not met and action to be taken**